## Time Tracking
Summary:
Hours: | 136
﻿What | How Long | When
Brainstorming im Team | 6 | September 3, 2025
Infrastructur Aufsetzen und Besprechen | 2 | September 10, 2025
Git Repo initialization & Approuch | 2 | September 17, 2025
Implementing JWT Token System | 5 | October 1, 2025
Worked on JWT Authentification & added en/decryption for passwords | 5 | October 2, 2025
JWT convert to HTTP Only Cookie | 5 | October 3, 2025
Implemented Login System in Frontend | 8 | October 16, 2025
Login & Register Modal | 9 | October 18, 2025
Fixing errors with severin | 2 | December 16, 2025
Fixing Darkmode Bug in Frontend | 3 | December 9, 2025
besprechung | 3 | December 22, 2025
fixing bugs | 4 | December 31, 2025
Implementing Seach View in Backend | 4 | January 7, 2026
Fixing bug with Darkmode in Frontend | 3 | January 4, 2026
Cleaning up Git Repo | 1 | January 16, 2026
besprechung | 4 | January 18, 2026
Implementing Search View and fixing some minor bugs | 3 | January 19, 2026
AWS Database Server Billing | 2 | November 18, 2025
AWS Database Server setup | 6 | September 13, 2025
Implemented Error Snackbar and Automatic Error Handling | 5 | January 20, 2026
Fixing Infrastructure Problems and trying to switch from aws to our own service | 7 | January 21, 2026
Working with Severin and Fixing Bugs | 4 | January 25, 2026
Implemented Success Snackbar | 2 | January 24, 2026
Fixed Login Bug | 5 | January 26, 2026
Connection to INCUS API established | 6 | January 27, 2026
Implementing some routes in backend incus api | 3 | January 29, 2026
Implemented VM Creation and Handling of Asyncronous Tasks | 9
Implemented Getting, Creation, Readings from Incus Backend. Implemented Operations from Incus too | 11 | January 30, 2026
Implemented Better Errorhandling for VM Creation and Getting VMs on the VM Page | 7 | January 31, 2026